## TeamH Kanban - Product Backlog
Title | URL | Milestone | Deliverable / Sprint | User Story | Story Type | Priority | Estimate (Story Points) | Status
Git Hub | https://github.com/COS420-Fall24/TeamH/issues/107 | Deliverable 2 | D2 | No | Requirements | Low | 1 | Todo / Sprint Backlog
Update tasks for use case descriptions | https://github.com/COS420-Fall24/TeamH/issues/89 | Deliverable 2 | D2 | No | Requirements | Low | 1 | In Progress
add new tasks to product backlog | https://github.com/COS420-Fall24/TeamH/issues/98 | Deliverable 2 | D2 | No | Requirements | Low | 1 | In Progress
Add new tasks to sprint backlog | https://github.com/COS420-Fall24/TeamH/issues/99 | Deliverable 2 | D2 | No | Requirements | Low | 1 | In Progress
Use Case Diagrams/Models and Descriptions | https://github.com/COS420-Fall24/TeamH/issues/104 | Deliverable 2 | D2 | No | Requirements | Low | 3 | In Progress
Product Backlog 2 | https://github.com/COS420-Fall24/TeamH/issues/105 | Deliverable 2 | D2 | No | Requirements | Low | 1 | In Progress
Sprint Backlog 2 | https://github.com/COS420-Fall24/TeamH/issues/106 | Deliverable 2 | D2 | No | Requirements | Low | 1 | In Progress
Touch up Sprint Review | https://github.com/COS420-Fall24/TeamH/issues/87 | Make corrections for D0 and D1 | D2 | No | Bug | Low | 1 | Quality Checking
New version of the application | https://github.com/COS420-Fall24/TeamH/issues/112 | Deliverable 2 | D2 | No | Requirements | Low | 2 | Quality Checking
User stories | https://github.com/COS420-Fall24/TeamH/issues/88 | Make corrections for D0 and D1 | D2 | No | Requirements | Low | 1 | Quality Checking
Edit Kanban task fields for each issue | https://github.com/COS420-Fall24/TeamH/issues/80 | Deliverable 2 | D2 | No | Requirements | Low | 1 | Quality Checking
SRS | https://github.com/COS420-Fall24/TeamH/issues/110 | Deliverable 2 | D2 | No | Requirements | Low | 1 | Quality Checking
Kanban | https://github.com/COS420-Fall24/TeamH/issues/108 | Deliverable 2 | D2 | No | Requirements | Low | 1 | Quality Checking
Architecture design | https://github.com/COS420-Fall24/TeamH/issues/111 | Deliverable 2 | D2 | No | Requirements | Low | 2 | Quality Checking
SRS - Creating Functional Requirements | https://github.com/COS420-Fall24/TeamH/issues/86 | Make corrections for D0 and D1 | D2 | No | Bug | Low | 1 | Quality Checking
Sprint review 2 | https://github.com/COS420-Fall24/TeamH/issues/109 | Deliverable 2 | D2 | No | Requirements | Low | 1 | Quality Checking
Describe "Find Scenario" use case | https://github.com/COS420-Fall24/TeamH/issues/94 | Deliverable 2 | D2 | No | Requirements | Low | 1 | Quality Checking
Describe "login" use case | https://github.com/COS420-Fall24/TeamH/issues/91 | Deliverable 2 | D2 | No | Requirements | Low | 1 | Quality Checking
Describe "Explain Code" use case | https://github.com/COS420-Fall24/TeamH/issues/90 | Deliverable 2 | D2 | No | Requirements | Low | 1 | Quality Checking
Describe "logout" use case | https://github.com/COS420-Fall24/TeamH/issues/92 | Deliverable 2 | D2 | No | Requirements | Low | 1 | Quality Checking
Describe "Adjust Explanation Scope" use case | https://github.com/COS420-Fall24/TeamH/issues/97 | Deliverable 2 | D2 | No | Requirements | Low | 1 | Quality Checking
Describe "Open Scenario" use case | https://github.com/COS420-Fall24/TeamH/issues/93 | Deliverable 2 | D2 | No | Requirements | Low | 1 | Quality Checking
Describe "Create Scenario" use case | https://github.com/COS420-Fall24/TeamH/issues/95 | Deliverable 2 | D2 | No | Requirements | Low | 1 | Quality Checking
Describe "Manage Scenario" use case | https://github.com/COS420-Fall24/TeamH/issues/96 | Deliverable 2 | D2 | No | Requirements | Low | 1 | Quality Checking
D3 sprint Review | https://github.com/COS420-Fall24/TeamH/issues/103 | D3 | Deliverable 3 | No | Requirements | Low | 1
Address product back log comments | https://github.com/COS420-Fall24/TeamH/issues/100 | D3 | Deliverable 3 | No | Requirements | Low | 1
Put project details in respective columns | https://github.com/COS420-Fall24/TeamH/issues/101 | D3 | Deliverable 3 | No | Requirements | Low | 1
Create Login screen | https://github.com/COS420-Fall24/TeamH/issues/113 | Deliverable 2 | D2 | No | Technical work | Medium | 1 | Quality Checking
Describe "Receive Feedback on Code" use case | https://github.com/COS420-Fall24/TeamH/issues/114 | Deliverable 2 | D2 | No | Requirements | Low | 1 | Quality Checking
Describe"Get Syntax Errors" use case | https://github.com/COS420-Fall24/TeamH/issues/115 | Deliverable 2 | D2 | No | Requirements | Low | 1 | Quality Checking
Descirbe "Change Language" use case | https://github.com/COS420-Fall24/TeamH/issues/116 | Deliverable 2 | D2 | No | Requirements | Low | 1 | Quality Checking
Describe "Delete Account" use case | https://github.com/COS420-Fall24/TeamH/issues/117 | Deliverable 2 | D2 | No | Requirements | Low | 1 | Quality Checking
Describe "Create Account" use case | https://github.com/COS420-Fall24/TeamH/issues/118 | Deliverable 2 | D2 | No | Requirements | Low | 1 | Quality Checking
As a beginner programmer, I want to input code snippets into a platform and receive real time explanations of how the code works. |  | 2 | 2 | yes | Requirements | High | 2
As a beginner programmer, I want to input code snippets into a platform and receive real time explanations of how the code works. |  | 2 | 2 | yes | Requirements | High | 2
As a user, I want to save explanations and concept links provided to me so that I can refer back to them while practicing. |  | 3 | 3 | yes | Requirements | Medium | 3
As a novice programmer, I want to adjust the level of detail in explanations I receive, so that I can progress from understanding basic concepts to more advanced coding techniques. |  | 2 | 2 | yes | Requirements | High | 2
As a developer, I want to add teammates' code and understand what it does so that I can build off it. |  | 4 | 4 | yes | Requirements | Medium | 3
As a beginner programmer, I want to have examples of code that are commented on, so that I will be able to understand how a snippet of code works. |  | 3 | 3 | yes | Requirements | Medium | 3
As a student, I want active feedback on my comprehension of a piece of code, so that I can reinforce my correct understanding and improve on what I don’t understand. |  | 2 | 2 | yes | Requirements | High | 2
As a teacher, I want to be able to create my own scenarios and feedback so that I can tailor the tool to fit my teaching style. |  | 5 | 5 | yes | Requirements | Medium | 3
I am a recently employed programmer who has no idea what my previous co-workers’ code means and they have no comments!!! I want an app that can help me understand what previous coworkers wrote. |  | 2 | 2 | yes | Requirements | High | 2
I am a journalist who is trying to do a report on code that someone made, but they are no longer around to provide understanding of the code.I want an app that helps me understand code without the need to hire a programmer for this job. |  | 2 | 2 | yes | Requirements | High | 2
As a gamer, I want to understand what makes my character move and act the way they do. |  | 3 | 3 | yes | Requirements | Low | 4
As a master programmer who is learning a new language, I want to be able to efficiently understand snippets of code provided to me from my other coworkers. |  | 3 | 3 | yes | Requirements | High | 2
As a junior dev beginning work with a mostly unfamiliar tech stack, I need help understanding the basic concepts behind these technologies in the context of my company. |  | 3 | 3 | yes | Requirements | Medium | 4
As a professor, I want to understand what exactly my student was trying to accomplish in their Python assignment because I am lost. |  | 3 | 3 | yes | Requirements | Low | 4
As a developer, I want to find alternative approaches to this problem I have already solved. |  | 4 | 4 | yes | Requirements | Low | 5
As a developer, I want to find human-curated resources for learning certain technologies that pertain to something I’m trying to build. |  | 5 | 5 | yes | Requirements | Medium | 3
As a beginner programmer, I want to be able to quickly and efficiently learn larger real world examples of commonly used code. |  | 5 | 5 | yes | Requirements | Medium | 5
As a beginner programmer, I want to be able to break large scale coding problems into smaller more manageable segments. |  | 4 | 4 | yes | Requirements | Medium | 3
As a professional programmer, I want to be able to have my coworkers view the code I am working on/trying to understand from a different computer so they can help me learn or learn with me. |  | 4 | 4 | yes | Requirements | Low | 5
As a beginner programmer, I want to have a database that stores all of the previous segments of code I have already worked on/learned so I can reuse the code to help me create larger, more complex programs. |  | 5 | 5 | yes | Requirements | Low | 5