## TeamH Kanban - Sprint Backlog
Title | URL | Status | Priority | Story Type | Estimate (Story Points) | Points Completed | Assignees | Contributors and % contribution | Quality Reviewer | Start date | End date (ready for QC by) | Deliverable / Sprint | Milestone
Git Hub | https://github.com/COS420-Fall24/TeamH/issues/107 | Todo / Sprint Backlog | Low | Requirements | 1 |  | antAmaine, Benji887, KemptonM, Linkaboy, obedappiah |  |  |  |  | D2 | Deliverable 2
Update tasks for use case descriptions | https://github.com/COS420-Fall24/TeamH/issues/89 | In Progress | Low | Requirements | 1 |  | antAmaine, Benji887, KemptonM, Linkaboy, obedappiah |  |  |  |  | D2 | Deliverable 2
add new tasks to product backlog | https://github.com/COS420-Fall24/TeamH/issues/98 | In Progress | Low | Requirements | 1 |  | antAmaine |  |  |  |  | D2 | Deliverable 2
Add new tasks to sprint backlog | https://github.com/COS420-Fall24/TeamH/issues/99 | In Progress | Low | Requirements | 1 |  | antAmaine |  |  |  |  | D2 | Deliverable 2
Use Case Diagrams/Models and Descriptions | https://github.com/COS420-Fall24/TeamH/issues/104 | In Progress | Low | Requirements | 3 | [6 empty] | D2 | Deliverable 2
Product Backlog 2 | https://github.com/COS420-Fall24/TeamH/issues/105 | In Progress | Low | Requirements | 1 | [6 empty] | D2 | Deliverable 2
Sprint Backlog 2 | https://github.com/COS420-Fall24/TeamH/issues/106 | In Progress | Low | Requirements | 1 | [6 empty] | D2 | Deliverable 2
Touch up Sprint Review | https://github.com/COS420-Fall24/TeamH/issues/87 | Quality Checking | Low | Bug | 1 |  | antAmaine, Benji887, KemptonM, Linkaboy, obedappiah |  |  |  |  | D2 | Make corrections for D0 and D1
New version of the application | https://github.com/COS420-Fall24/TeamH/issues/112 | Quality Checking | Low | Requirements | 2 |  | obedappiah |  |  |  |  | D2 | Deliverable 2
User stories | https://github.com/COS420-Fall24/TeamH/issues/88 | Quality Checking | Low | Requirements | 1 |  | antAmaine, Benji887, KemptonM, Linkaboy, obedappiah |  |  |  |  | D2 | Make corrections for D0 and D1
Edit Kanban task fields for each issue | https://github.com/COS420-Fall24/TeamH/issues/80 | Quality Checking | Low | Requirements | 1 |  | antAmaine, Benji887, KemptonM, Linkaboy, obedappiah |  |  |  |  | D2 | Deliverable 2
SRS | https://github.com/COS420-Fall24/TeamH/issues/110 | Quality Checking | Low | Requirements | 1 | [6 empty] | D2 | Deliverable 2
Kanban | https://github.com/COS420-Fall24/TeamH/issues/108 | Quality Checking | Low | Requirements | 1 |  | antAmaine |  |  |  |  | D2 | Deliverable 2
Architecture design | https://github.com/COS420-Fall24/TeamH/issues/111 | Quality Checking | Low | Requirements | 2 | [6 empty] | D2 | Deliverable 2
SRS - Creating Functional Requirements | https://github.com/COS420-Fall24/TeamH/issues/86 | Quality Checking | Low | Bug | 1 |  | antAmaine, Benji887, KemptonM, Linkaboy, obedappiah |  |  |  |  | D2 | Make corrections for D0 and D1
Sprint review 2 | https://github.com/COS420-Fall24/TeamH/issues/109 | Quality Checking | Low | Requirements | 1 | [6 empty] | D2 | Deliverable 2
Describe "Find Scenario" use case | https://github.com/COS420-Fall24/TeamH/issues/94 | Quality Checking | Low | Requirements | 1 |  | antAmaine |  |  |  |  | D2 | Deliverable 2
Describe "login" use case | https://github.com/COS420-Fall24/TeamH/issues/91 | Quality Checking | Low | Requirements | 1 |  | antAmaine |  |  |  |  | D2 | Deliverable 2
Describe "Explain Code" use case | https://github.com/COS420-Fall24/TeamH/issues/90 | Quality Checking | Low | Requirements | 1 |  | KemptonM, obedappiah |  |  |  |  | D2 | Deliverable 2
Describe "logout" use case | https://github.com/COS420-Fall24/TeamH/issues/92 | Quality Checking | Low | Requirements | 1 |  | antAmaine |  |  |  |  | D2 | Deliverable 2
Describe "Adjust Explanation Scope" use case | https://github.com/COS420-Fall24/TeamH/issues/97 | Quality Checking | Low | Requirements | 1 |  | antAmaine |  |  |  |  | D2 | Deliverable 2
Describe "Open Scenario" use case | https://github.com/COS420-Fall24/TeamH/issues/93 | Quality Checking | Low | Requirements | 1 |  | antAmaine |  |  |  |  | D2 | Deliverable 2
Describe "Create Scenario" use case | https://github.com/COS420-Fall24/TeamH/issues/95 | Quality Checking | Low | Requirements | 1 |  | antAmaine |  |  |  |  | D2 | Deliverable 2
Describe "Manage Scenario" use case | https://github.com/COS420-Fall24/TeamH/issues/96 | Quality Checking | Low | Requirements | 1 |  | antAmaine |  |  |  |  | D2 | Deliverable 2
Create Login screen | https://github.com/COS420-Fall24/TeamH/issues/113 | Quality Checking | Medium | Technical work | 1 |  | obedappiah |  |  |  |  | D2 | Deliverable 2
Describe "Receive Feedback on Code" use case | https://github.com/COS420-Fall24/TeamH/issues/114 | Quality Checking | Low | Requirements | 1 | [6 empty] | D2 | Deliverable 2
Describe"Get Syntax Errors" use case | https://github.com/COS420-Fall24/TeamH/issues/115 | Quality Checking | Low | Requirements | 1 | [6 empty] | D2 | Deliverable 2
Descirbe "Change Language" use case | https://github.com/COS420-Fall24/TeamH/issues/116 | Quality Checking | Low | Requirements | 1 | [6 empty] | D2 | Deliverable 2
Describe "Delete Account" use case | https://github.com/COS420-Fall24/TeamH/issues/117 | Quality Checking | Low | Requirements | 1 | [6 empty] | D2 | Deliverable 2
Describe "Create Account" use case | https://github.com/COS420-Fall24/TeamH/issues/118 | Quality Checking | Low | Requirements | 1 | [6 empty] | D2 | Deliverable 2