## Sheet1
See column descriptions in other tab
ID | User Story | Sprint Number | Story Priority | Story Status | Story Points
1 | Establish user stories to create backlogs and kanban | 1 | High | Done | 1
2 | Establish requirements so we can complete the srs | 1 | High | Done | 4
3 | Complete kanban so we can organize our workflow and assigned tasks | 1 | High | Done | 3
4 | Create mockup of UI navigation for how user will navigate through app | 1 | High | Done | 3
5 | Prepare initial code/software so there is some source code to go off of | 1 | High | Done | 1
6 | As a beginner programmer, I want to input code snippets into a platform and receive real time explanations of how the code works. | 2 | High | Waiting | 2
7 | As a beginner programmer, I want to input code snippets into a platform and receive real time explanations of how the code works. | 2 | High | Waiting | 2
8 | As a user, I want to save explanations and concept links provided to me so that I can refer back to them while practicing. | 3 | Medium | Waiting | 3
9 | As a novice programmer, I want to adjust the level of detail in explanations I receive, so that I can progress from understanding basic concepts to more advanced coding techniques. | 2 | High | Waiting | 2
10 | As a developer, I want to add teammates' code and understand what it does so that I can build off it. | 4 | Medium | Waiting | 3
11 | As a beginner programmer, I want to have examples of code that are commented on, so that I will be able to understand how a snippet of code works. | 3 | Medium | Waiting | 3
12 | As a student, I want active feedback on my comprehension of a piece of code, so that I can reinforce my correct understanding and improve on what I don’t understand. | 2 | High | Waiting | 2
13 | As a teacher, I want to be able to create my own scenarios and feedback so that I can tailor the tool to fit my teaching style. | 5 | Medium | Waiting | 3
14 | I am a recently employed programmer who has no idea what my previous co-workers’ code means and they have no comments!!! I want an app that can help me understand what previous coworkers wrote. | 2 | High | Waiting | 2
15 | I am a journalist who is trying to do a report on code that someone made, but they are no longer around to provide understanding of the code.I want an app that helps me understand code without the need to hire a programmer for this job. | 2 | High | Waiting | 2
16 | As a gamer, I want to understand what makes my character move and act the way they do. | 3 | Low | Waiting | 4
17 | As a master programmer who is learning a new language, I want to be able to efficiently understand snippets of code provided to me from my other coworkers. | 3 | High | Waiting | 2
18 | As a junior dev beginning work with a mostly unfamiliar tech stack, I need help understanding the basic concepts behind these technologies in the context of my company. | 3 | Medium | Waiting | 4
19 | As a professor, I want to understand what exactly my student was trying to accomplish in their Python assignment because I am lost. | 3 | Low | Waiting | 4
20 | As a developer, I want to find alternative approaches to this problem I have already solved. | 4 | Low | Waiting | 5
21 | As a developer, I want to find human-curated resources for learning certain technologies that pertain to something I’m trying to build. | 5 | Medium | Waiting | 3
22 | As a beginner programmer, I want to be able to quickly and efficiently learn larger real world examples of commonly used code. | 5 | Medium | Waiting | 5
23 | As a beginner programmer, I want to be able to break large scale coding problems into smaller more manageable segments. | 4 | Medium | Waiting | 3
24 | As a professional programmer, I want to be able to have my coworkers view the code I am working on/trying to understand from a different computer so they can help me learn or learn with me. | 4 | Low | Waiting | 5
25 | As a beginner programmer, I want to have a database that stores all of the previous segments of code I have already worked on/learned so I can reuse the code to help me create larger, more complex programs. | 5 | Low | Waiting | 5

## Description of Columns
ID: unique # for each story * Story: Contains the user stories (one story per row) in priority order ▪ Formatted as “As a <user role>, I need to <feature needed> because of <benefit>. o Sprint: The story’s sprint number (when it gets implemented) o Priority: H (high), M (medium), L (low) o Status: Backlog, To Do, IP (in progress), QC (quality checking), D (done) o Estimate / Story Points: Number of story points gives an indication of the difficulty of the story’s development and testing as well as possibly an estimate of the number of hours to design, implement, and test the story.
The basic idea of story points is a story with 3 points is 3x the effort as a 1 point story, 2 points is 2x the effort, etc. In general without much experience it's hard for you to estimate relative feature sizes. Just do your best. Here's more information https://www.mountaingoatsoftware.com/blog/what-are-story-points
Note there is another option this year to export this document instead from Github projects, see https://discord.com/channels/1280324227790278737/1280324228255711263/1291882302460399657