## Sprint i
ID | User Story | Task ID | Story Tasks | Sprint Number | Sprint Goal | Story Type | Story Points | Story Points Completed | Names and Contribution Percentage
1 | Establish user stories to create backlogs and kanban | 1 | Create list of user stories | 1 | Create documentation, create initial code of application, and design wireframes of UI | Requirements | 1 | 1 | Ben 20%, Kempton 20%, Obed 20%, Bryce 20%, Anthony 20%
|  | 1.1 | Edit user stories based on feedback given |  |  | Requirements | 1 | 1 | Ben 20%, Kempton 20%, Obed 20%, Bryce 20%, Anthony 20%
|  | 1.2 | Decide which user stories will go into product/sprint backlog |  |  | Technical Work | 1 | 1 | Ben 20%, Kempton 20%, Obed 20%, Bryce 20%, Anthony 20%
2 | Establish requirements so we can complete the srs | 2 | Create list of functional and non-functional requirements |  |  | Requirements | 2 | 2 | Ben 20%, Kempton 20%, Obed 20%, Bryce 20%, Anthony 20%
|  | 2.1 | Create list of project features |  |  | Technical Work | 2 | 2 | Ben 20%, Kempton 20%, Obed 20%, Bryce 20%, Anthony 20%
|  | 2.2 | Use requirements to complete SRS document |  |  | Requirements | 2 | 2 | Ben 20%, Kempton 20%, Obed 20%, Bryce 20%, Anthony 20%
3 | Complete kanban so we can organize our workflow and assigned tasks | 3 | Complete product backlog |  |  | Requirements | 1 | 1 | Ben 100%
|  | 3.1 | Update project description |  |  | Requirements | 1 | 1 | Ben 20%, Kempton 20%, Obed 20%, Bryce 20%, Anthony 20%
|  | 3.2 | Complete sprint review document |  |  | Requirements | 1 | 1 | Obed 50%, Anthony 25%% Kempton 25%
|  | 3.3 | Check that all group members have read quality checking policy |  |  | Technical Work | 1 | 1 | Ben 20%, Kempton 20%, Obed 20%, Bryce 20%, Anthony 20%
|  | 3.4 | Assign group members documents to quality check |  |  | Technical Work | 1 | 1 | Obed 100%
|  | 3.5 | Complete sprint backlog |  |  | Requirements | 1 | 1 | Ben 80% Kempton 5%,Obed 5%, Anthony 5%, Bryce 5%
|  | 3.6 | Move tasks to kanban |  |  | Technical Work | 1 | 1 | Ben 20%, Kempton 20%, Obed 20%, Bryce 20%, Anthony 20%
|  | 3.7 | Assign tasks to their respective group members on kanban |  |  | Technical Work | 1 | 1 | Ben 20%, Kempton 20%, Obed 20%, Bryce 20%, Anthony 20%
4 | Create mockup of UI navigation for how user will navigate through app | 4 | Design important wireframes of application |  |  | Requirements | 2 | 2 | Anthony 100%
|  | 4.1 | Plan how user will navigate through different UIs within application |  |  | Knowledge Acquisition | 1 | 1 | Anthony 100%
|  | 4.2 | Plan UIs needed for application |  |  | Knowledge Acquisition | 2 | 2 | Ben 20%, Kempton 20%, Obed 20%, Bryce 20%, Anthony 20%
5 | Prepare initial code/software so there is some source code to go off of | 5 | Choose environment and language we will us for application |  |  | Requirements | 2 | 2 | Ben 20%, Kempton 20%, Obed 20%, Bryce 20%, Anthony 20%
|  | 5.1 | Create starter code to mimic UI for important features of application |  |  | Technical Work | 4 | 4 | Anthony 100%
|  | 5.2 | Test to make sure code works on all group members' devices |  |  | Technical Work | 2 | 2 | Ben 20%, Kempton 20%, Obed 20%, Bryce 20%, Anthony 20%

## Column Description
o Sprint Goal and Number. o Story copied from the project backlog or a sprint task story. o Story Type: F (functional), NF (non-functional) with a subtype: B (bug), T (technical work), KA(knowledge acquisition, technical or design/users). o Story Points. o Story Points Completed. o Team Member Names and percentage of contribution to the story.
Note there is another option this year to export this document instead from Github projects, see https://discord.com/channels/1280324227790278737/1280324228255711263/1291882302460399657